## SIT Bug Tracking Sheet
Issue ID | Browser | DBLX REQ ID | Test Case ID | Reported date | Close Date | Issue Type | Status | Severity | Priority | Issue Title | Steps to reproduce the issue | Expected result | Actual Result | Bug Filename | Test Data used | Created By | Assigned to | Resolved by | Fix Date | Reopen Date | Development team comment | DigitalBlocks Comments
Issue_001 | Chrome | REQ_ID_ _001 | TC002 | 2024-08-08 |  | Functional | New | Medium | P1 | Unable to Slide Between Images of Selected Product | 1. Navigate to Home page 2. Click on a product 3. Switch between the two buttons at bottom of product's image | The system should successfully display all product images by sliding | The system unsuccessfully unable to slide between all product images | https://drive.google.com/file/d/1lwHm5BAhxbr1N3_OJqyJps0D28NgqRUo/view?usp=sharing | N / A | Mohamed Karim | Digital Blocks
Issue_002 | Chrome | REQ_ID_ _002 | TC005 | 2024-08-08 |  | Functional | New | Medium | P3 | Filtered Category Shows Some Irrelevant Products When Navigating Back | 1. Navigate to Home page 2. Select a type of product from "Categories" list. 3.Navigate to next page 4.Navigate back to previous page | Products relevant to the chosen category are displayed on the previous page. | The system display irrelevant product to filtered category on previous page | https://drive.google.com/file/d/1rVRjdT8V5h0S0G28HgdLJjk3N3k0e7v2/view?usp=sharing | N / A | Mohamed Karim | Digital Blocks
Issue_003 | Chrome | REQ_ID_ _003 | TC008 | 2024-08-08 |  | Functional | New | High | P1 | Clicked Product on Slider Does not Navigates to the Product's Page | 1. Navigate to Home page 2. Select a product in the slider | The system displays information of the selected product on the product page after clicking it in the slider. | The system is unable to navigate to the product page of the selected product from the slider | https://drive.google.com/file/d/1CyqrXH2rt0KWv39CqLw1iExb3u341Kv7/view?usp=sharing | N / A | Mohamed Karim | Digital Blocks
Issue_004 | Chrome | REQ_ID_ _005 | TC011 | 2024-12-08 |  | Functional | New | High | P1 | Contact Message Accepts Empty Data Fields | 1. Navigate to Contact 2. Leave Contact Email Blank 3. Leave Contact Name Blank 4. Leave Message Blank | The system should reject empty message and request user to fill required fields | The system unsuccessfully accept empty message and raised confirmation message | https://drive.google.com/file/d/1LYMaw2uUotRLqEfRVvcl5dCONSFQv5bi/view?usp=sharing | 1. Email: "" 2. Name: "" 3. Message: "" | Mohamed Karim | Digital Blocks
Issue_005 | Chrome | REQ_ID_ _005 | TC012 | 2024-12-08 |  | Functional | New | High | P1 | Contact Message Accepts Invalid Email of Digits only | 1. Navigate to Contact 2. Fill Contact Email Blank 3. Fill Contact Name Blank 4. Fill Message Blank | The system should raise error message that email field accepts email format only | The system unsuccessfully accept message with invalid email containing only digits and raised a confirmation message. | https://drive.google.com/file/d/1hG5DrlMQB02pU5l9QB28LJInGvc-OAU3/view?usp=sharing | 1. Email: "101333" 2. Name: "Mohamed Karim" 3. Message: "I have a complain." | Mohamed Karim | Digital Blocks
Issue_006 | Chrome | REQ_ID_ _005 | TC013 | 13/8/2024 |  | Functional | New | Low | P3 | Contact Message Accepts Invalid Name That Contain Digits only | 1. Navigate to Contact 2. Fill Contact Email 3. Fill Contact Name 4. Fill Message | The should system raise error message that Name field accepts Letters only. | The system accept the message and raise confirmation message | https://drive.google.com/file/d/18Oxer-ENtEgTwXS3vXRrh2ru0d6VZvED/view?usp=sharing | 1. Email: "mohamedkarim.office@gmail.com" 2. Name: "22321" 3. Message: "I have a complain." | Mohamed Karim | Digital Blocks
Issue_007 | Chrome | REQ_ID_ _005 | TC014 | 13/8/2024 |  | Functional | New | Low | P3 | Contact Message Accepts Invalid Name That Contain Special Character | 1. Navigate to Contact 2. Fill Contact Email 3. Fill Contact Name 4. Fill Message | The system should don't accept message and raise message name should not contain special characters | The system accept the message and raise confirmation message | https://drive.google.com/file/d/17J1efwlDurig-1HiiMtTRtTsfYmKfYH-/view?usp=drive_link | 1. Email: "mohamedkarim.office@gmail.com" 2. Name: "!@#$" 3. Message: "I have a complain." | Mohamed Karim | Digital Blocks
Issue_008 | Chrome | REQ_ID_ _005 | TC015 | 13/8/2024 |  | Functional | New | Low | P4 | Contact Message Accepts an empty message content | 1. Navigate to Contact 2. Fill Contact Email 3. Fill Contact Name 4. Leave Message Field Blank | The system should raise error message that message field should not be empty | The system accepts a message with empty message content and provides a confirmation message. | https://drive.google.com/file/d/1_0fFoHPy6ONNTga_ZN64JSjenA5BZhcu/view?usp=drive_link | 1. Email: "mohamedkarim.office@gmail.com" 2. Name: "Mohamed Karim" 3. Message: "" | Mohamed Karim | Digital Blocks
Issue_009 | Chrome | REQ_ID_ _010 | TC024 | 13/8/2024 |  | Functional | New | Medium | P3 | Cart Checkout Accept Invalid Name Containing Digits | 1. Add a Product to Cart 2. Verify Product is Added to Cart 3. Place Order 4. Fill Name Field 5. Fill Country Field 6. Fill City Field 7. Fill Credit Car Field 8. Fill Month Field 9. Fill Year Field 10. Click on: "Purchase" Button | The system should raise error message that name field accepts letters only | The system accept the cart checkout with invalid name contain digits, and provide message that order placed successfully | https://drive.google.com/file/d/1mhY7dhEMAUpHfwzkYOEi6U_mBRwyjSfQ/view?usp=drive_link | Name: "453" Country: "Egypt" City: "Cairo" Credit Card: "1234567891123456" Month: "7" Year: "2028" | Mohamed Karim | Digital Blocks
Issue_010 | Chrome | REQ_ID_ _010 | TC025 | 13/8/2024 |  | Functional | New | Medium | P3 | Cart Checkout Accept Invalid Country Containing Special Character | 1. Add a Product to Cart 2. Verify Product is Added to Cart 3. Place Order 4. Fill Name Field 5. Fill Country Field 6. Fill City Field 7. Fill Credit Car Field 8. Fill Month Field 9. Fill Year Field 10. Click on: "Purchase" Button | The system should not place order with invalid country containing special character | The system accept the invalid country containing special character and provide message that order placed successfully | https://drive.google.com/file/d/16aM97zP9yByS_yIyfx_j4TIKh9ku9kC-/view?usp=sharing | Name: "Mohamed Karim" Country: "Egypt$%@" City: "Cairo" Credit Card: "1234567891123456" Month: "7" Year: "2028" | Mohamed Karim | Digital Blocks
Issue_011 | Chrome | REQ_ID_ _010 | TC026 | 13/8/2024 |  | Functional | New | Medium | P3 | Cart Checkout Accept Invalid Country Containing Digits | 1. Add a Product to Cart 2. Verify Product is Added to Cart 3. Place Order 4. Fill Name Field 5. Fill Country Field 6. Fill City Field 7. Fill Credit Car Field 8. Fill Month Field 9. Fill Year Field 10. Click on: "Purchase" Button | The system should raise error message country field accepts letters only | The system accept the invalid country containing digits and provide message that order placed successfully | https://drive.google.com/file/d/1ncFViJfpbTHg2gPP7txT0_ROPe_6qrj5/view?usp=sharing | Name: "Mohamed Karim" Country: "01055" City: "Cairo" Credit Card: "1234567891123456" Month: "7" Year: "2028" | Mohamed Karim | Digital Blocks
Issue_012 | Chrome | REQ_ID_ _010 | TC027 | 13/8/2024 |  | Functional | New | Medium | P3 | Cart Checkout Accept Invalid City Containing Special Character | 1. Add a Product to Cart 2. Verify Product is Added to Cart 3. Place Order 4. Fill Name Field 5. Fill Country Field 6. Fill City Field 7. Fill Credit Car Field 8. Fill Month Field 9. Fill Year Field 10. Click on: "Purchase" Button | The system should raise an error message stating that the city field accepts letters only and discard the order. | The system accept the invalid city containing special character and provide message that order placed successfully | https://drive.google.com/file/d/1EfFIGw1ooCrLZmB8IQYZ0e3G5N8MOsu8/view?usp=sharing | Name: "Mohamed Karim" Country: "Egypt" City: "Cairo%@" Credit Card: "1234567891123456" Month: "7" Year: "2028" | Mohamed Karim | Digital Blocks
Issue_013 | Chrome | REQ_ID_ _010 | TC028 | 13/8/2024 |  | Functional | New | Medium | P3 | Cart Checkout Accept Invalid City Containing Digits | 1. Add a Product to Cart 2. Verify Product is Added to Cart 3. Place Order 4. Fill Name Field 5. Fill Country Field 6. Fill City Field 7. Fill Credit Car Field 8. Fill Month Field 9. Fill Year Field 10. Click on: "Purchase" Button | The system should raise an error message stating that the city field accepts letters only and discard the order. | The system accept the invalid city containing digits and provide message that order placed successfully | https://drive.google.com/file/d/1x7_jq_-Gb7vN9-qD7WHezk8SUUKAIbTa/view?usp=sharing | Name: "Mohamed Karim" Country: "Egypt" City: "5.5" Credit Card: "1234567891123456" Month: "7" Year: "2028" | Mohamed Karim | Digital Blocks
Issue_014 | Chrome | REQ_ID_ _010 | TC029 | 13/8/2024 |  | Functional | New | Medium | P3 | Cart Checkout Accepts Invalid Credit Card with Insufficient Digits | 1. Add a Product to Cart 2. Verify Product is Added to Cart 3. Place Order 4. Fill Name Field 5. Fill Country Field 6. Fill City Field 7. Fill Credit Car Field 8. Fill Month Field 9. Fill Year Field 10. Click on: "Purchase" Button | The system should raise an error message stating that the credit card field accepts 16 digits only and discard the order. | The system accept the invalid credit card containing insufficient digits and provide message that order placed successfully | https://drive.google.com/file/d/1rXsRZ6tTL6u-HEdemYIvCPhgUtGcoVD9/view?usp=sharing | Name: "Mohamed Karim" Country: "Egypt" City: "Cairo" Credit Card: "123456" Month: "7" Year: "2028" | Mohamed Karim | Digital Blocks
Issue_015 | Chrome | REQ_ID_ _010 | TC030 | 13/8/2024 |  | Functional | New | Medium | P3 | Cart Checkout Accepts Invalid Credit Card Containing String | 1. Add a Product to Cart 2. Verify Product is Added to Cart 3. Place Order 4. Fill Name Field 5. Fill Country Field 6. Fill City Field 7. Fill Credit Car Field 8. Fill Month Field 9. Fill Year Field 10. Click on: "Purchase" Button | The system should not accept the order, and raise error message credit card can not contain string | The system accept invalid credit card contains string, and placed order | https://drive.google.com/file/d/1kyuU6P0MI8FNQTorBVBwrM8PtOXdjC7i/view?usp=sharing | Name: "Mohamed Karim" Country: "Egypt" City: "Cairo" Credit Card: "Visa" Month: "7" Year: "2028" | Mohamed Karim | Digital Blocks
Issue_016 | Chrome | REQ_ID_ _010 | TC031 | 13/8/2024 |  | Functional | New | Medium | P3 | Cart Checkout Accepts Invalid Credit Card Containing Special Character | 1. Add a Product to Cart 2. Verify Product is Added to Cart 3. Place Order 4. Fill Name Field 5. Fill Country Field 6. Fill City Field 7. Fill Credit Car Field 8. Fill Month Field 9. Fill Year Field 10. Click on: "Purchase" Button | The system should not accept the order, and raise error message credit card can not contain special characters | The system accept an invalid credit card containing special character, and provide message that order places successfully | https://drive.google.com/file/d/151HkHA0cPmxdmOe2bNECiDtoQHHsDvux/view?usp=sharing | Name: "Mohamed Karim" Country: "Egypt" City: "Cairo" Credit Card: "!@" Month: "7" Year: "2028" | Mohamed Karim | Digital Blocks
Issue_017 | Chrome | REQ_ID_ _010 | TC032 | 13/8/2024 |  | Functional | New | Medium | P3 | Cart Checkout Accepts an Invalid Credit Card Month That is Out of Range. | 1. Add a Product to Cart 2. Verify Product is Added to Cart 3. Place Order 4. Fill Name Field 5. Fill Country Field 6. Fill City Field 7. Fill Credit Car Field 8. Fill Month Field 9. Fill Year Field 10. Click on: "Purchase" Button | The system should raise error message that is an Invalid Month, and discard the order | The system accepts an invalid month that is out of range and places the order. | https://drive.google.com/file/d/1QYimB_G90_7UZXts64UcwsjL_N_fv_C-/view?usp=sharing | Name: "Mohamed Karim" Country: "Egypt" City: "Cairo" Credit Card: "1234567891123456" Month: "17" Year: "2028" | Mohamed Karim | Digital Blocks
Issue_018 | Chrome | REQ_ID_ _010 | TC033 | 13/8/2024 |  | Functional | New | Medium | P3 | Cart Checkout Accepts an Invalid Credit Card Month Containing Special Character. | 1. Add a Product to Cart 2. Verify Product is Added to Cart 3. Place Order 4. Fill Name Field 5. Fill Country Field 6. Fill City Field 7. Fill Credit Car Field 8. Fill Month Field 9. Fill Year Field 10. Click on: "Purchase" Button | The system should not accept the order, and raise error message month can not contain special characters | The system accepts an invalid month that contain special character and places the order. | https://drive.google.com/file/d/1p5_kxaZS7AodynR-w3sERJvYdLOayqu-/view?usp=sharing | Name: "Mohamed Karim" Country: "Egypt" City: "Cairo" Credit Card: "1234567891123456" Month: "$!" Year: "2028" | Mohamed Karim | Digital Blocks
Issue_019 | Chrome | REQ_ID_ _010 | TC034 | 13/8/2024 |  | Functional | New | Medium | P4 | Cart Checkout Accepts an Invalid Year Containing Special Character. | 1. Add a Product to Cart 2. Verify Product is Added to Cart 3. Place Order 4. Fill Name Field 5. Fill Country Field 6. Fill City Field 7. Fill Credit Car Field 8. Fill Month Field 9. Fill Year Field 10. Click on: "Purchase" Button | The system should not accept the order, and raise error message year can not contain special characters | The system accepts an invalid year that contain special character and places the order. | https://drive.google.com/file/d/13FpVBsB-xxrqjT0x6I7U-Dc1pOHLO5XX/view?usp=sharing | Name: "Mohamed Karim" Country: "Egypt" City: "Cairo" Credit Card: "1234567891123456" Month: "7" Year: "20@8" | Mohamed Karim | Digital Blocks
Issue_020 | Chrome | REQ_ID_ _010 | TC035 | 13/8/2024 |  | Functional | New | Medium | P5 | Cart Checkout Accepts an Invalid Year that is out of range . | 1. Add a Product to Cart 2. Verify Product is Added to Cart 3. Place Order 4. Fill Name Field 5. Fill Country Field 6. Fill City Field 7. Fill Credit Car Field 8. Fill Month Field 9. Fill Year Field 10. Click on: "Purchase" Button | The system should not accept the order, and raise error message year can not hold value out of range | The system accepts an invalid year that is out of range and places the order. | https://drive.google.com/file/d/1j8VGkqV0SywwrbS7HntRmV4wK6DlB7sm/view?usp=sharing | Name: "Mohamed Karim" Country: "Egypt" City: "Cairo" Credit Card: "1234567891123456" Month: "7" Year: "20" | Mohamed Karim | Digital Blocks

## Report Defects Dashboard (hidden)
Defect- Status
| Status | Defects
| New | 20 | [6 empty] | Duplicate | 0
| Under Investigation | 0
| Fixing | 0
| Ready for Retest | 0
| Re Open | 0
| Need Clarification | 0
| Rejected | 0
| Can't Reproduce | 0
| Pending deployment | 0
| Not An Issue | 0 | [5 empty] | Overall Defects | 20
| Closed | 0
| Total | 20
without Close | Total # Open Defects | 20 |  |  |  |  | 74 | 74
| Severity Vs Status | New | Under Investigation | Fixing | Need Clarification | Rejected | Ready for Retest | Can't Reproduce | Re Open | Total
| Show Stopper | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| High | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Medium | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
| Low | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Total | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
Open Defects Ownership
| Assigned To | New | Under Investigation | Fixing | Re Open | Need Clarification | Rejected | Ready for Retest | Not An Issue | Pending deployment | Can't Reproduce | Total
| Digital Blocks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GAHAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| eFinance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Severity Vs Status | New | Under Investigation | Fixing | Re Open | Need Clarification | Rejected | Ready for Retest | Not An Issue | Pending deployment | Closed | Can't Reproduce | Total
| Show Stopper | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| High | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Medium | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
| Low | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Total | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
| Assigned To | Show Stopper | High | Medium | Low | Total
| Digital Blocks | 0 | 3 | 14 | 3 | 20
| SC | 0 | 0 | 0 | 0 | 0
| GAHAR | 0 | 0 | 0 | 0 | 0
| eFinance | 0 | 0 | 0 | 0 | 0
| Total | 0 | 3 | 14 | 3 | 20 |  | Overall Open Defects | 20
| Status VS Severity | Show Stopper | High | Medium | Low | Total
| New | 0 | 3 | 14 | 3 | 20
| Under Investigation | 0 | 0 | 0 | 0 | 0
| Fixing | 0 | 0 | 0 | 0 | 0
| Ready for Retest | 0 | 0 | 0 | 0 | 0
| Re Open | 0 | 0 | 0 | 0 | 0
| Need Clarification | 0 | 0 | 0 | 0 | 0
| Rejected | 0 | 0 | 0 | 0 | 0
| Can't Reproduce | 0 | 0 | 0 | 0 | 0
| Not An Issue | 0 | 0 | 0 | 0 | 0
| Pending deployment | 0 | 0 | 0 | 0 | 0
| Total | 0 | 3 | 14 | 3 | 20
Issue Type Count
| Issue Type | Show Stopper | High | Medium | Low | Total
| Functional | 0 | 3 | 14 | 3 | 20
| UI ( Interface ) | 0 | 0 | 0 | 0 | 0
| Requirement | 0 | 0 | 0 | 0 | 0
| Environment | 0 | 0 | 0 | 0 | 0
| Bonita | 0 | 0 | 0 | 0 | 0
| Enhancement | 0 | 0 | 0 | 0 | 0
| Total | 0 | 3 | 14 | 3 | 20

## Sameh (hidden)
Issue ID | Source | Environment | Test Case ID | Reported Date | Issue Type | Status | Severity | Closure Reason | Priority | Issue Title | Steps to reproduce the issue | Expected result | Actual Result | BugFileName | Test Data used | Created By | Assigned to | Fix Date | Reopen Date | Issue Impact | Remarks | Attachments | Development team comment | DigitalBlocks Comments | Phase | Stage
Issue _218 |  | VF |  | 2022-07-03 | UI ( Interface ) | New | Low |  | P3 | 218- UI issue when when tried to download the registration request | 1- Open the E portal 2- Create new facility 3- Set the specialty to set 5 records 4- Go though the cycle till print the registration form |  | The section of “مقدم الطلب” display in 2 pages | https://drive.google.com/file/d/155OGdOn4w1uccxEt_4XRBFehLTmmIqz6/view?usp=sharing | E portal :clinic-smart@g.com pass: Eng@jaguar22 | GAHAR | SC
issue _219 |  | VF |  | 2022-07-03 | Functional | New | Low |  | P2 | 219- the fields set أخرى in eporal display in bonita "اخرى" | 1- Open the E portal 2- Create new facility 3- set the data to set “اخرى” in owner and specialty and any field contain "اخرى" 4- open bonita and take the created task | the fields should display اخرى | all fields which set at اخري displayed in bonita as other | https://drive.google.com/file/d/1-abaZgOva_QvokX3BOHxtDJUxnB4tcy7/view?usp=sharing | E portal :clinic-smart@g.com pass: Eng@jaguar22 | GAHAR | SC
Issue _220 |  | VF |  | 2022-08-03 | Functional | New | low |  | p3 | 220- wrong validation message when set data in “اسم العائله\اللقب” | 1- log in E portal 2- create new facility and ser the require data 3- from the data form of البيانات الرئيسيه 4- from the field “اسم العائله\اللقب ” set the value “اسم العائله\اللقب ” | a validation message display that the اسم العائله\اللقب is not correct | a validation message display that the "الاسم الاخير " is not correct | https://drive.google.com/file/d/14C2LQQrOLp8bLOMV6XAI5H17zrqQlk04/view?usp=sharing |  | VF | sc
issue_221 |  | VF |  | 2022-08-03 | Functional | New | low |  | p3 | 221- wrong vaildation message when set vaild website | 1- log in E portal 2- create new facility and ser the require data 3- from the data form of البيانات الرئيسيه 4- set the website to be : www.f.g 5- walk thought the cycle till submit the request 6- open bonita 7- click take of the assign task | no validation message should be display | validation message display that the web is not correct | https://drive.google.com/file/d/19pmeFt-ql7Ii9lNGpyXn_YeXPduf8l8L/view?usp=sharing |  | vf | sc

## Lists
Severity
Show Stopper
High
Medium
Low
Environment
UAT
UAT 2
VF
Priority
P1
P2
P3
P4
Status
New
Configuration
Under Investigation
Fixing
Ready for Retest
Question
Not An Issue
Re Open
Pending deployment
Duplicate
Closed
Need Clarification
Rejected
Can't Reproduce
Created By
Mohamed Karim
Talent 2
Talent 3
Talent 4
Talent 5
Stakeholder 1
Stakeholder 2
Stakeholder 3
Assigned To
Digital Blocks
MCIT
1
2
3
4
5
6
7
8
9
Source
Chrome
Firefox
Microsoft Edge
Reason
Retest Failed
Fixed
Duplicate
Invalid Test Case
Accepted Change
Resolved
Invalid Test Data
Requirement Issue
Denied Change Request
Not an Issue
Configuration issue
Deferred
Stage
SIT
Regression
UAT
E2E
Issue Type
Functional
Enhancement
UI ( Interface )
Requirement
Environment
Phase
Phase 1
Phase 2
Stage / Module

## status (hidden)
Issue_130 | unusual behavior from the system not related to a certain tc
Issues 162 | retrieve irrelevant data
Issues 163 | retrieve irrelevant data
Issue_113 | UI issues in the registration certificate.
Issue_109 | Enhancement
Issue_191 | unusual behavior from the system

## GAHAR SIT Execution Completion (hidden)
Severity Vs Status | New | Under Investigation | Fixing | Need Clarification | Rejected | Ready for Retest | Re Open | Closed | Total
Show Stopper | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
High | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Medium | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
Low | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Total | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20

## Sherif (hidden)
| Test Cases Group | Show Stopper | High | Medium | Low
| BMS_ADMIN | 0 | 0 | 0 | 0
| Beneficiary_Registration | 0 | 0 | 0 | 0
| Beneficiary Modifications | 0 | 0 | 0 | 0
| Super Admin,Admin Roles | 0 | 0 | 0 | 0
| Premium Scenarios | 0 | 0 | 0 | 0
| Enrollment Officer | 0 | 0 | 0 | 0
| BMS- EMS Integration | 0 | 0 | 0 | 0
| Family Registration | 0 | 0 | 0 | 0
| Total | 0 | 0 | 0 | 0
Status | #
New | #REF!
Under Investigation | #REF!
Fixing | #REF!
Ready for Retest | #REF!
Re Open | #REF!
Not an Issue(IQVIA) | #REF!
Need Clarification | #REF!
Can't Reproduce | #REF!
Assigned To | #
Digital Blocks | 20
IQVIA | 0
UHIA | 0
VF | 0
Status VS Severity | Show Stopper | High | Medium | Low
New | 0 | 3 | 14 | 3
Under Investigation | 0 | 0 | 0 | 0
Fixing | 0 | 0 | 0 | 0
Ready for Retest | 0 | 0 | 0 | 0
Re Open | 0 | 0 | 0 | 0
Closed (Fixed) | 0 | 0 | 0 | 0
Closed (Not an Issue) | 0 | 0 | 0 | 0
Not an Issue(IQVIA) | 0 | 0 | 0 | 0
Need Clarification | 0 | 0 | 0 | 0
Can't Reproduce | 0 | 0 | 0 | 0
Total | 0 | 3 | 14 | 3 | 0
Assigned To | New | Under Investigation | Fixing | Ready for Retest | Re Open | Not an Issue(IQVIA) | Need Clarification | Can't Reproduce
IQVIA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UHIA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0